## 📋 Test Plan Summary
EAM Platform — Phase 0 Foundations Test Plan & Execution Tracker
Project |  |  | Enterprise Asset Management (EAM) Web Application
Phase |  |  | Phase 0 — Foundations
Document |  |  | Test Plan v1.0
Prepared by |  |  | QA Team
Date |  |  | 23 May 2026
Total Tests |  |  | 166
Status Legend
⬜ NOT RUN |  | ✅ PASS |  | ❌ FAIL |  | ⏭️ SKIP |  | 🔄 IN PROGRESS |  | 🚫 BLOCKED
Workstream | Ref | Total Tests | Pass | Fail | Skip | Not Run | Pass % | Status
P0-1 User Management & Identity | P0-1 | 26 | 0 | 0 | 0 | 26 |  | 0% | ⬜ NOT RUN
P0-2 Application Configuration Engine | P0-2 | 19 | 0 | 0 | 0 | 19 |  | 0% | ⬜ NOT RUN
P0-3 Schema Extension & Workflow Builder | P0-3 | 18 | 0 | 0 | 0 | 18 |  | 0% | ⬜ NOT RUN
P0-4 Integration Framework | P0-4 | 13 | 0 | 0 | 0 | 13 |  | 0% | ⬜ NOT RUN
P0-5 Attachment Service + Virus Scan | P0-5 | 13 | 0 | 0 | 0 | 13 |  | 0% | ⬜ NOT RUN
P0-6 Reporting Engine & BI Adapters | P0-6 | 14 | 0 | 0 | 0 | 14 |  | 0% | ⬜ NOT RUN
P0-7 Dashboard & Collaboration | P0-7 | 14 | 0 | 0 | 0 | 14 |  | 0% | ⬜ NOT RUN
P0-8 Email Notification Framework | P0-8 | 16 | 0 | 0 | 0 | 16 |  | 0% | ⬜ NOT RUN
Integration Sprint | INT | 33 | 0 | 0 | 0 | 33 |  | 0% | ⬜ NOT RUN
TOTALS |  | 166 | 0 | 0 | 0 | 166 | 0% | ⬜ NOT RUN

## 🔐 P0-1 Identity
EAM Phase 0 — P0-1 User Management & Identity ¦ Test Cases
Workstream: P0-1 • Pass: =COUNTIF(G5:G5000,"✅ PASS") ¦ Fail: =COUNTIF(G5:G5000,"❌ FAIL") ¦ Total: =COUNTA(B5:B5000)
# | Test ID | Category | Type | Priority | Test Title | Status | Preconditions | Test Steps | Expected Result | Actual Result | Tester | Date Tested | Notes / Defect Ref
Local Authentication
1 | P0-1-U-001 | Local Authentication | Unit | P1-Critical | Password hashing uses Argon2id | ⬜ NOT RUN | packages/auth installed | 1. Call hashPassword('Test@1234') 2. Call verifyPassword('Test@1234', hash) | Hash produced; verify returns true; plain text not stored
2 | P0-1-U-002 | Local Authentication | Unit | P1-Critical | Password policy enforcement — min length | ⬜ NOT RUN | Policy: minLength=10 | 1. Attempt register with password 'Short1!' | Validation error returned; user not created
3 | P0-1-U-003 | Local Authentication | Unit | P1-Critical | Password policy — complexity rules | ⬜ NOT RUN | Policy: requireUppercase, requireNumber, requireSpecial | 1. Try 'alllowercase1!' 2. Try 'NoNumber!!' 3. Try 'Valid@Pass1' | First two rejected with specific error; third accepted
4 | P0-1-U-004 | Local Authentication | Unit | P2-High | Account lockout after N failed logins | ⬜ NOT RUN | lockoutAfterFailures=5 | 1. POST /auth/login with wrong password 5 times 2. Try correct password on 6th attempt | 6th attempt returns 429 with lockout_until timestamp
5 | P0-1-I-005 | Local Authentication | Integration | P1-Critical | Full register → login → refresh → logout cycle | ⬜ NOT RUN | Postgres running via Testcontainers | 1. POST /auth/register 2. POST /auth/login 3. POST /auth/refresh 4. POST /auth/logout 5. GET /auth/me with old token | Each step returns correct response; step 5 returns 401
6 | P0-1-I-006 | Local Authentication | Integration | P1-Critical | Refresh token rotation — old token invalidated | ⬜ NOT RUN | Valid session exists | 1. POST /auth/refresh → get new token pair 2. POST /auth/refresh with OLD refresh token | Step 2 returns 401; old token is revoked
7 | P0-1-I-007 | Local Authentication | Integration | P2-High | Password reset flow end-to-end | ⬜ NOT RUN | SMTP mock (Mailhog) configured | 1. POST /auth/password/reset-request 2. Extract token from email 3. POST /auth/password/reset 4. Login with new password | Login succeeds with new password; old password rejected
Multi-Factor Authentication
1 | P0-1-M-001 | Multi-Factor Authentication | Integration | P1-Critical | TOTP setup — QR code + verify | ⬜ NOT RUN | User logged in | 1. POST /auth/mfa/setup 2. Generate TOTP code from secret 3. POST /auth/mfa/verify-setup with code | users.mfa_enabled=true; 10 recovery codes returned (plaintext, once)
2 | P0-1-M-002 | Multi-Factor Authentication | Integration | P1-Critical | MFA login challenge flow | ⬜ NOT RUN | User has MFA enabled | 1. POST /auth/login → expect {mfa_required:true, mfa_session_token} 2. Generate TOTP code 3. POST /auth/mfa/challenge with code + session token | Step 3 returns full JWT pair; mfa_verified=true in JWT claims
3 | P0-1-M-003 | Multi-Factor Authentication | Integration | P2-High | MFA recovery code usage | ⬜ NOT RUN | User has MFA enabled; has recovery codes | 1. POST /auth/mfa/challenge with valid recovery_code instead of TOTP | Login succeeds; used recovery code marked used_at; cannot be reused
4 | P0-1-M-004 | Multi-Factor Authentication | Integration | P2-High | Per-role MFA enforcement | ⬜ NOT RUN | Role 'Admin' has require_mfa=true; user in Admin role without MFA enabled | 1. User completes password login (no MFA) 2. Access admin-only endpoint | Step 2 returns 401 with error code MFA_REQUIRED
5 | P0-1-M-005 | Multi-Factor Authentication | Unit | P3-Medium | MFA secret encrypted at rest | ⬜ NOT RUN | User has MFA enabled | 1. Query users table directly for mfa_secret column | Value is encrypted ciphertext; not plain TOTP secret
AD / LDAP Synchronisation
1 | P0-1-L-001 | AD / LDAP Synchronisation | Integration | P1-Critical | LDAP user sync creates EAM user | ⬜ NOT RUN | Mock LDAP server running; identity provider configured | 1. Trigger POST /admin/identity-providers/:id/sync 2. Query /admin/users | User from LDAP appears in EAM; auth_source=LDAP; attributes mapped correctly
2 | P0-1-L-002 | AD / LDAP Synchronisation | Integration | P1-Critical | LDAP group membership synced | ⬜ NOT RUN | Mock LDAP has group 'EAM-Supervisors' with test user | 1. Trigger sync 2. GET /admin/groups | Group created in EAM; user is member; group can be assigned EAM role
3 | P0-1-L-003 | AD / LDAP Synchronisation | Integration | P2-High | Delta sync — only changed records fetched | ⬜ NOT RUN | Full sync completed; one user modified in LDAP | 1. Modify user attribute in mock LDAP 2. Trigger sync 3. Check audit log | Sync log shows 1 updated (not all users); modifyTimestamp used correctly
4 | P0-1-L-004 | AD / LDAP Synchronisation | Integration | P2-High | Deactivated LDAP user disabled in EAM | ⬜ NOT RUN | User exists in EAM from previous sync | 1. Remove user from LDAP 2. Trigger sync 3. Attempt login as that user | User.is_active=false; login returns 403
5 | P0-1-L-005 | AD / LDAP Synchronisation | Integration | P3-Medium | LDAP sync audit log records outcome | ⬜ NOT RUN | After a sync with 3 adds, 1 update | 1. Check audit_logs table after sync | Entry with action=LDAP_SYNC, metadata.added=3, metadata.updated=1
SSO — SAML 2.0 & OIDC
1 | P0-1-S-001 | SSO — SAML 2.0 & OIDC | E2E | P1-Critical | SAML 2.0 SP-initiated login | ⬜ NOT RUN | Mock SAML IdP running; provider configured in EAM | 1. Navigate to /auth/saml/:id/login 2. Complete mock IdP flow 3. Callback to EAM | User upserted in EAM; JWT session issued; auth_source=SAML
2 | P0-1-S-002 | SSO — SAML 2.0 & OIDC | E2E | P2-High | OIDC login with PKCE against mock IdP | ⬜ NOT RUN | OIDC provider configured with discovery URL | 1. Navigate to /auth/oidc/:id/login 2. Complete OIDC flow 3. Callback | Tokens exchanged; user info fetched; EAM session issued
3 | P0-1-S-003 | SSO — SAML 2.0 & OIDC | Integration | P2-High | SSO claim mapping — groups auto-assigned | ⬜ NOT RUN | SAML response includes group attribute 'EAM-Admins' | 1. Login via SAML 2. Check user's groups in EAM | User added to EAM group 'EAM-Admins' automatically
4 | P0-1-S-004 | SSO — SAML 2.0 & OIDC | API | P3-Medium | Admin can disable SSO provider | ⬜ NOT RUN | Active SSO provider exists | 1. PUT /admin/identity-providers/:id {is_active:false} 2. Try SSO login | SSO login redirects with error; local auth still works
RBAC & User Admin
1 | P0-1-R-001 | RBAC & User Admin | Integration | P1-Critical | Role assignment grants permissions | ⬜ NOT RUN | User without any role | 1. Create role with permission 'workorders:read' 2. Assign role to user 3. Access GET /workorders | Access granted immediately (within same session via token refresh)
2 | P0-1-R-002 | RBAC & User Admin | Integration | P1-Critical | Effective permissions — union of multiple roles | ⬜ NOT RUN | User has Role A (read) and Role B (write) | 1. GET /admin/users/:id/effective-permissions | Result includes both read and write permissions
3 | P0-1-R-003 | RBAC & User Admin | Integration | P2-High | Admin deactivates user — all sessions invalidated | ⬜ NOT RUN | User has 2 active sessions | 1. PUT /admin/users/:id {is_active:false} 2. Make request with both tokens | Both tokens return 401
4 | P0-1-R-004 | RBAC & User Admin | Security | P1-Critical | Impersonation is audit logged | ⬜ NOT RUN | Admin user with impersonate permission | 1. POST /admin/users/:id/impersonate 2. Perform an action 3. Check audit_logs | audit_logs shows original_admin_id and impersonated_user_id on every action
5 | P0-1-R-005 | RBAC & User Admin | API | P2-High | Group-based role inheritance | ⬜ NOT RUN | Group assigned role 'Technician' | 1. Add user to group 2. Check user's effective permissions | User inherits all permissions from 'Technician' role via group

## ⚙️ P0-2 Config Engine
EAM Phase 0 — P0-2 Application Configuration Engine ¦ Test Cases
Workstream: P0-2 • Pass: =COUNTIF(G5:G5000,"✅ PASS") ¦ Fail: =COUNTIF(G5:G5000,"❌ FAIL") ¦ Total: =COUNTA(B5:B5000)
# | Test ID | Category | Type | Priority | Test Title | Status | Preconditions | Test Steps | Expected Result | Actual Result | Tester | Date Tested | Notes / Defect Ref
Field Management
1 | P0-2-F-001 | Field Management | Integration | P1-Critical | Add custom text field to Asset entity | ⬜ NOT RUN | Admin auth token; Asset entity exists | 1. POST /admin/config/entities/Asset/fields {field_key:'asset_tag', field_type:'TEXT', is_required_global:true} 2. GET /admin/config/entities/Asset/fields | Field returned in list; column custom__asset_tag exists in assets table
2 | P0-2-F-002 | Field Management | Integration | P1-Critical | Custom field persists data correctly | ⬜ NOT RUN | asset_tag field created | 1. POST /assets {asset_tag:'EQ-001', ...other required fields} 2. GET /assets/:id | asset_tag value 'EQ-001' returned in response
3 | P0-2-F-003 | Field Management | API | P2-High | All field types can be created | ⬜ NOT RUN | Asset entity | Create one field of each type: TEXT, NUMBER, DATE, DATETIME, BOOLEAN, PICKLIST, LOOKUP, ATTACHMENT | All fields created; each stores and retrieves correct data type
4 | P0-2-F-004 | Field Management | API | P2-High | Field deactivation hides field from UI (not deleted) | ⬜ NOT RUN | Custom field exists with data | 1. PATCH field {is_active:false} 2. GET form layout | Field absent from form; column still in DB; data preserved
Server-Side Validation
1 | P0-2-V-001 | Server-Side Validation | API | P1-Critical | Global required field blocks save at API level | ⬜ NOT RUN | asset_tag field has is_required_global=true | 1. POST /assets without asset_tag field | 422 returned with {field:'asset_tag', message:'Required'} — not just a UI warning
2 | P0-2-V-002 | Server-Side Validation | API | P1-Critical | Conditional required — field required only when condition met | ⬜ NOT RUN | Field rule: asset_tag required when priority=CRITICAL | 1. POST /assets {priority:'HIGH'} — no asset_tag 2. POST /assets {priority:'CRITICAL'} — no asset_tag | Step 1 succeeds; step 2 returns 422
3 | P0-2-V-003 | Server-Side Validation | API | P2-High | Regex validation on text field | ⬜ NOT RUN | Field has validation_rules: {regex:'^EQ-[0-9]{3}$'} | 1. POST /assets {asset_tag:'WRONG'} 2. POST /assets {asset_tag:'EQ-001'} | Step 1 returns 422 with regex error; step 2 succeeds
4 | P0-2-V-004 | Server-Side Validation | Security | P1-Critical | Validation cannot be bypassed via API (front-end bypass attempt) | ⬜ NOT RUN | Required field configured | 1. Make direct API call omitting required field (no front-end) | Server returns 422; required field not optional at API level
Form Designer
1 | P0-2-D-001 | Form Designer | E2E | P2-High | Create 3-column form layout via designer | ⬜ NOT RUN | Admin logged in; Form Designer page open | 1. Drag 3 fields into a row 2. Save layout 3. Open entity form as regular user | Form renders 3 columns on desktop
2 | P0-2-D-002 | Form Designer | E2E | P2-High | Form collapses to 1 column on phone viewport | ⬜ NOT RUN | 3-column layout saved | 1. Open entity form 2. Resize browser to 375px width | Form shows 1 column; all fields still accessible
3 | P0-2-D-003 | Form Designer | E2E | P3-Medium | Role-specific form variant | ⬜ NOT RUN | Two roles: Technician, Manager | 1. Create separate layouts for each role 2. Login as each role | Each role sees their configured layout; Technician does not see Manager-only fields
4 | P0-2-D-004 | Form Designer | E2E | P3-Medium | Preview mode in designer shows correct breakpoints | ⬜ NOT RUN | Admin in Form Designer | 1. Click Desktop / Tablet / Phone preview toggles | Preview iframe renders correct column count for each breakpoint
Picklist Management
1 | P0-2-P-001 | Picklist Management | API | P2-High | Create cascading picklist (parent-child) | ⬜ NOT RUN | Admin auth | 1. Create picklist 'AssetClass' with values [Mechanical, Electrical] 2. Create picklist 'AssetSubClass' with parent_value links 3. Filter by parent value | Only child values of selected parent returned
2 | P0-2-P-002 | Picklist Management | API | P2-High | Per-org picklist override | ⬜ NOT RUN | Multi-org tenant | 1. Global picklist has value 'Standard' 2. Create org-level override with extra value 'Custom' 3. Fetch picklist as Org A user | Org A user sees both 'Standard' and 'Custom'; Org B user sees only 'Standard'
3 | P0-2-P-003 | Picklist Management | API | P3-Medium | Effective-date picklist value | ⬜ NOT RUN | Picklist value with effective_to in the past | 1. Fetch picklist values | Expired value not returned in active list; historical records still display it
Config Versioning & Export/Import
1 | P0-2-CV-001 | Config Versioning & Export/Import | API | P2-High | Config version created on field change | ⬜ NOT RUN | Existing field definition | 1. PUT /admin/config/entities/Asset/fields/:id {label:'New Label'} 2. GET /admin/config/versions?entity=field_definition&entityId=:id | Version entry exists with old and new state snapshot
2 | P0-2-CV-002 | Config Versioning & Export/Import | API | P2-High | Rollback config version | ⬜ NOT RUN | Version history with 2 versions | 1. POST /admin/config/versions/:v1id/rollback 2. GET field definition | Field definition matches v1 snapshot; custom DB column unchanged
3 | P0-2-CV-003 | Config Versioning & Export/Import | API | P2-High | Export + import config JSON | ⬜ NOT RUN | Dev environment with custom fields | 1. GET /admin/config/export?entities[]=Asset 2. POST /admin/config/import to clean Test env | All field and form definitions present in Test; no errors
4 | P0-2-CV-004 | Config Versioning & Export/Import | API | P3-Medium | Import conflict detection | ⬜ NOT RUN | Test env already has field 'asset_tag' | 1. Import config that also defines 'asset_tag' with different type | Conflict flagged in import response; no silent overwrite

## 🔄 P0-3 Workflow
EAM Phase 0 — P0-3 Schema Extension & Workflow Builder ¦ Test Cases
Workstream: P0-3 • Pass: =COUNTIF(G5:G5000,"✅ PASS") ¦ Fail: =COUNTIF(G5:G5000,"❌ FAIL") ¦ Total: =COUNTA(B5:B5000)
# | Test ID | Category | Type | Priority | Test Title | Status | Preconditions | Test Steps | Expected Result | Actual Result | Tester | Date Tested | Notes / Defect Ref
Schema Extension (DDL)
1 | P0-3-S-001 | Schema Extension (DDL) | Integration | P1-Critical | Add column via API — column exists in DB | ⬜ NOT RUN | Asset table exists; Postgres running | 1. POST /admin/config/entities/Asset/fields (triggers DDL) 2. Query information_schema.columns for custom__new_field | Column exists with correct type; migration logged as SUCCESS
2 | P0-3-S-002 | Schema Extension (DDL) | Integration | P1-Critical | DDL is idempotent (IF NOT EXISTS) | ⬜ NOT RUN | Custom column already exists | 1. Call addColumn for same field again | No error; no duplicate column; migration log shows SKIPPED or SUCCESS
3 | P0-3-S-003 | Schema Extension (DDL) | Integration | P2-High | Advisory lock prevents concurrent DDL on same table | ⬜ NOT RUN | Two concurrent addColumn requests for 'assets' table | 1. Fire 2 simultaneous addColumn requests 2. Check schema_migrations | Both succeed eventually; no corruption; lock contention handled gracefully
4 | P0-3-S-004 | Schema Extension (DDL) | Integration | P2-High | Index created for searchable field | ⬜ NOT RUN | Field created with is_searchable=true | 1. Query pg_indexes for custom__field_name on assets table | Index exists; created with CONCURRENTLY (non-blocking)
5 | P0-3-S-005 | Schema Extension (DDL) | Integration | P2-High | Soft-drop renames column with _deleted_ prefix | ⬜ NOT RUN | Custom column exists | 1. DELETE /admin/config/entities/Asset/fields/:id 2. Check column name in DB | Column renamed to custom___deleted__field_name; data preserved
Workflow Engine — Node Types
1 | P0-3-W-001 | Workflow Engine — Node Types | Unit | P1-Critical | DECISION node — correct branch on SQL condition | ⬜ NOT RUN | WorkflowEngine unit test | 1. Create workflow: START → DECISION (totalcost>100000 → Finance path, else → Manager path) → END 2. Run with context {totalcost:150000} | Finance path taken
2 | P0-3-W-002 | Workflow Engine — Node Types | Unit | P1-Critical | DECISION node — alternate branch | ⬜ NOT RUN | Same workflow | 1. Run with context {totalcost:80000} | Manager path taken
3 | P0-3-W-003 | Workflow Engine — Node Types | Integration | P1-Critical | TASK node creates workflow_task record | ⬜ NOT RUN | Workflow with TASK node assigned to role 'Supervisor' | 1. Start workflow instance 2. Query workflow_tasks | Task record in PENDING status; assigned_to_role='Supervisor'
4 | P0-3-W-004 | Workflow Engine — Node Types | Integration | P1-Critical | APPROVAL node — approve action advances workflow | ⬜ NOT RUN | Task in PENDING state | 1. Call advanceTask(taskId, userId, 'APPROVE', 'Looks good') 2. Check instance state | Task status=COMPLETED; next node activated; history entry recorded
5 | P0-3-W-005 | Workflow Engine — Node Types | Integration | P1-Critical | APPROVAL node — reject routes to reject path | ⬜ NOT RUN | Workflow with reject_path configured | 1. Call advanceTask with action='REJECT' | Workflow takes reject_path; reject notification fired
6 | P0-3-W-006 | Workflow Engine — Node Types | Unit | P2-High | SUPERVISOR assignment resolves via manager_id chain | ⬜ NOT RUN | User with manager_id set | 1. Create TASK node with assignment_type=SUPERVISOR 2. Start workflow as user X | Task assigned to user X's manager (resolved via users.manager_id)
7 | P0-3-W-007 | Workflow Engine — Node Types | Integration | P2-High | SLA escalation — task reassigned after due_at | ⬜ NOT RUN | TASK node with SLA 5 minutes; escalation_role='Senior Manager' | 1. Start workflow; do NOT complete task 2. Advance time past due_at 3. Run BullMQ job manually | Task status=ESCALATED; new task created for Senior Manager; history records escalation
8 | P0-3-W-008 | Workflow Engine — Node Types | Integration | P2-High | Workflow versioning — in-flight uses old version | ⬜ NOT RUN | v1 published; v2 published afterwards | 1. Start workflow (uses v1) 2. Publish v2 3. Advance task on v1 instance | v1 instance completes using v1 definition; new instance after step 2 uses v2
9 | P0-3-W-009 | Workflow Engine — Node Types | Integration | P2-High | PARALLEL_SPLIT — multiple tasks created simultaneously | ⬜ NOT RUN | Workflow with parallel split to 2 paths | 1. Start workflow 2. Query workflow_tasks | 2 tasks created simultaneously; both in PENDING
10 | P0-3-W-010 | Workflow Engine — Node Types | Integration | P2-High | SYNCHRONISE — waits for all parallel tasks | ⬜ NOT RUN | Workflow: split → 2 tasks → sync → end | 1. Complete task 1 only 2. Check instance state | Instance still RUNNING; END not reached until task 2 also completed
Workflow Designer UI
1 | P0-3-D-001 | Workflow Designer UI | E2E | P2-High | Create and publish workflow via designer | ⬜ NOT RUN | Admin in Workflow Designer | 1. Drag START → DECISION → TASK → END nodes 2. Configure condition on DECISION 3. Click Publish | Workflow saved to workflow_definitions with version=1 and is_active=true
2 | P0-3-D-002 | Workflow Designer UI | E2E | P2-High | Simulate mode — correct branch highlighted | ⬜ NOT RUN | Published workflow with DECISION node | 1. Click Simulate 2. Enter test values {totalcost:200000} 3. Click Next | Correct branch highlighted in canvas; no workflow_instances created in DB
3 | P0-3-D-003 | Workflow Designer UI | E2E | P3-Medium | Workflow binding to entity trigger | ⬜ NOT RUN | Published workflow | 1. Set workflow to trigger on SR_CREATED for ServiceRequest entity 2. Create SR | Workflow instance auto-starts on SR creation

## 🔌 P0-4 Integration
EAM Phase 0 — P0-4 Integration Framework ¦ Test Cases
Workstream: P0-4 • Pass: =COUNTIF(G5:G5000,"✅ PASS") ¦ Fail: =COUNTIF(G5:G5000,"❌ FAIL") ¦ Total: =COUNTA(B5:B5000)
# | Test ID | Category | Type | Priority | Test Title | Status | Preconditions | Test Steps | Expected Result | Actual Result | Tester | Date Tested | Notes / Defect Ref
REST Adapter
1 | P0-4-R-001 | REST Adapter | Integration | P2-High | REST adapter executes GET request and maps response | ⬜ NOT RUN | Mock HTTP server (msw) running | 1. Configure REST connection to mock server 2. Create job to GET /test-endpoint 3. Run job | Response received; fields mapped to EAM record per mapping_config; run_log=SUCCESS
2 | P0-4-R-002 | REST Adapter | Integration | P2-High | REST adapter with OAuth2 client credentials | ⬜ NOT RUN | Mock OAuth2 token endpoint | 1. Configure connection with auth_type=OAUTH2_CLIENT_CREDENTIALS 2. Run job | Token fetched; Bearer header set on subsequent calls; token cached until expiry
3 | P0-4-R-003 | REST Adapter | Integration | P2-High | REST adapter retry on 5xx error | ⬜ NOT RUN | Mock server returns 503 twice then 200 | 1. Configure retry_attempts=3 2. Run job | Job succeeds on 3rd attempt; retry attempts logged
4 | P0-4-R-004 | REST Adapter | Integration | P3-Medium | REST adapter test connection | ⬜ NOT RUN | Admin auth | 1. POST /admin/integrations/connections/:id/test | Returns {success:true, latency_ms} if reachable; {success:false, error} if not
SFTP Adapter
1 | P0-4-S-001 | SFTP Adapter | Integration | P2-High | SFTP inbound — pick up CSV and create records | ⬜ NOT RUN | Mock SFTP server with test CSV file | 1. Configure SFTP inbound job 2. Run job 3. Check EAM entity records | CSV rows mapped to EAM records; file archived/removed per config; run_log shows record count
2 | P0-4-S-002 | SFTP Adapter | Integration | P3-Medium | SFTP outbound — generate CSV from query | ⬜ NOT RUN | EAM has work order records | 1. Configure outbound job with query selecting open WOs 2. Run job | CSV file uploaded to SFTP path; filename has timestamp
Webhook Outbound
1 | P0-4-W-001 | Webhook Outbound | Integration | P1-Critical | Webhook fires on entity status change | ⬜ NOT RUN | Webhook subscription active; listener server running | 1. Change WO status 2. Check webhook listener | JSON payload delivered within 5s; X-EAM-Signature header present and verifiable
2 | P0-4-W-002 | Webhook Outbound | Integration | P1-Critical | HMAC signature verification | ⬜ NOT RUN | Webhook payload received | 1. Compute HMAC-SHA256 of payload body using shared secret 2. Compare to header value | Signatures match; payload not tampered
3 | P0-4-W-003 | Webhook Outbound | Integration | P2-High | Webhook retry on delivery failure | ⬜ NOT RUN | Listener returns 500 | 1. Fire webhook 2. Listener returns 503 three times | 3 retries with exponential backoff (1s, 2s, 4s); dead-lettered after 3rd failure; admin alerted
4 | P0-4-W-004 | Webhook Outbound | Integration | P2-High | Admin disables webhook subscription | ⬜ NOT RUN | Active subscription | 1. Set subscription is_active=false 2. Trigger entity change | No webhook delivery; no delivery log entry for that subscription
Integration Admin UI
1 | P0-4-A-001 | Integration Admin UI | E2E | P3-Medium | Create connection, test, save | ⬜ NOT RUN | Admin in Integration admin UI | 1. Create REST connection with valid URL 2. Click Test 3. Save | Test result shown; connection saved; appears in connections list
2 | P0-4-A-002 | Integration Admin UI | E2E | P3-Medium | View run history and error log | ⬜ NOT RUN | Job has been run with one failure | 1. Navigate to job run history | Both successful and failed runs shown; error details expandable
3 | P0-4-A-003 | Integration Admin UI | E2E | P3-Medium | Manual trigger of scheduled job | ⬜ NOT RUN | Admin on job detail page | 1. Click 'Run Now' | Job queued immediately; run log entry created; status updates in UI

## 📎 P0-5 Attachments
EAM Phase 0 — P0-5 Attachment Service & Virus Scanning ¦ Test Cases
Workstream: P0-5 • Pass: =COUNTIF(G5:G5000,"✅ PASS") ¦ Fail: =COUNTIF(G5:G5000,"❌ FAIL") ¦ Total: =COUNTA(B5:B5000)
# | Test ID | Category | Type | Priority | Test Title | Status | Preconditions | Test Steps | Expected Result | Actual Result | Tester | Date Tested | Notes / Defect Ref
Upload Pipeline
1 | P0-5-U-001 | Upload Pipeline | Integration | P1-Critical | Standard upload flow — presign → upload → confirm | ⬜ NOT RUN | MinIO running; document type 'General' configured | 1. POST /attachments/presign {documentType:'General', filename:'test.pdf'} 2. PUT file to presigned URL 3. POST /attachments/:id/confirm | Attachment record created; scan_status=PENDING then CLEAN; download URL works
2 | P0-5-U-002 | Upload Pipeline | API | P1-Critical | File extension rejected if not in allowed list | ⬜ NOT RUN | Document type allows only [pdf, jpg] | 1. POST /attachments/presign {filename:'report.xlsx'} | 422 returned; no presigned URL issued; no S3 object created
3 | P0-5-U-003 | Upload Pipeline | API | P2-High | File size limit enforced at presign | ⬜ NOT RUN | Document type max_size=5MB | 1. POST /attachments/presign {fileSize:10000000} | 422 returned with size_limit_exceeded error
4 | P0-5-U-004 | Upload Pipeline | Integration | P2-High | SHA-256 checksum recorded | ⬜ NOT RUN | After successful upload | 1. GET /attachments/:id/metadata | checksum_sha256 field populated with correct hash of uploaded file
Virus Scanning
1 | P0-5-V-001 | Virus Scanning | Integration | P1-Critical | EICAR test file triggers QUARANTINE action | ⬜ NOT RUN | ClamAV running; document type virus_scan_action=QUARANTINE | 1. Upload EICAR test string as .txt file 2. Wait for scan worker 3. GET /attachments/:id/metadata | scan_status=INFECTED; file moved to quarantine prefix in S3; download returns 403
2 | P0-5-V-002 | Virus Scanning | Integration | P1-Critical | EICAR file triggers REJECT action | ⬜ NOT RUN | Document type virus_scan_action=REJECT | 1. Upload EICAR test string | File deleted from S3; attachment.deleted_at set; uploader notification sent
3 | P0-5-V-003 | Virus Scanning | Integration | P2-High | EICAR file triggers ALERT action — file still accessible | ⬜ NOT RUN | Document type virus_scan_action=ALERT | 1. Upload EICAR test string 2. GET /attachments/:id/download | scan_status=INFECTED but download still returns URL; admin notification sent
4 | P0-5-V-004 | Virus Scanning | Integration | P2-High | virus_scan_enabled=false skips scan queue | ⬜ NOT RUN | Document type virus_scan_enabled=false | 1. Upload any file 2. GET /attachments/:id/metadata immediately | scan_status=null or N/A; file immediately downloadable; no BullMQ job queued
5 | P0-5-V-005 | Virus Scanning | Integration | P2-High | ClamAV unavailable with BLOCK fallback | ⬜ NOT RUN | ClamAV service stopped; fallback_action=BLOCK | 1. POST /attachments/presign + confirm | Upload blocked with service_unavailable error; file not stored
Attachment Library & Versioning
1 | P0-5-L-001 | Attachment Library & Versioning | Integration | P2-High | Same file linked to two entity records — single S3 object | ⬜ NOT RUN | Existing attachment | 1. POST /attachments/:id/link {entityType:'WorkOrder',entityId:'WO-002'} 2. Check S3 object count | One S3 object; two attachment_links records; storage_key identical
2 | P0-5-L-002 | Attachment Library & Versioning | Integration | P2-High | Deleting one link does not delete S3 object | ⬜ NOT RUN | Attachment linked to WO-001 and WO-002 | 1. DELETE /attachments/:id?entityType=WorkOrder&entityId=WO-001 2. GET /attachments for WO-002 | WO-001 link removed; WO-002 attachment still present and downloadable
3 | P0-5-L-003 | Attachment Library & Versioning | Integration | P2-High | Upload new version of existing attachment | ⬜ NOT RUN | Attachment v1 exists | 1. Upload new file with version_of=:existingId 2. GET /attachments/:id/versions | Two version records; download default returns v2; v1 still accessible
4 | P0-5-L-004 | Attachment Library & Versioning | API | P3-Medium | Retention policy flag — attachment marked for review | ⬜ NOT RUN | Document type retention_days=30; attachment uploaded 31 days ago (set created_at in DB) | 1. Run retention check job | Attachment flagged with expires_at in the past; appears in admin retention review list

## 📊 P0-6 Reporting
EAM Phase 0 — P0-6 Reporting Engine & BI Adapters ¦ Test Cases
Workstream: P0-6 • Pass: =COUNTIF(G5:G5000,"✅ PASS") ¦ Fail: =COUNTIF(G5:G5000,"❌ FAIL") ¦ Total: =COUNTA(B5:B5000)
# | Test ID | Category | Type | Priority | Test Title | Status | Preconditions | Test Steps | Expected Result | Actual Result | Tester | Date Tested | Notes / Defect Ref
Query Builder & Security
1 | P0-6-Q-001 | Query Builder & Security | Unit | P1-Critical | tenant_id always injected into queries | ⬜ NOT RUN | ReportQueryBuilder unit test | 1. Build query for 'work_orders' subject 2. Inspect generated SQL | WHERE clause always includes tenant_id = $1 parameter; never string-concatenated
2 | P0-6-Q-002 | Query Builder & Security | Security | P1-Critical | SQL injection attempt via filter field | ⬜ NOT RUN | Report with user-controlled filter value | 1. Pass filter value: '; DROP TABLE work_orders; --' | QueryBuilder rejects or escapes; no DDL executed; 400 returned
3 | P0-6-Q-003 | Query Builder & Security | Security | P1-Critical | Tenant A cannot access Tenant B data | ⬜ NOT RUN | Two tenants with work orders | 1. Run report as Tenant A user 2. Check results | Only Tenant A work orders in results; Tenant B rows absent
4 | P0-6-Q-004 | Query Builder & Security | Unit | P2-High | All filter operators work correctly | ⬜ NOT RUN | QueryBuilder unit tests | Test EQUALS, NOT_EQUALS, CONTAINS, STARTS_WITH, IN, BETWEEN, IS_NULL operators | Each generates correct parameterised SQL clause
Report Designer & Export
1 | P0-6-D-001 | Report Designer & Export | E2E | P2-High | Non-developer creates report without SQL | ⬜ NOT RUN | Admin in Report Designer | 1. Select 'work_orders' subject 2. Drag 3 fields 3. Add filter (status=OPEN) 4. Preview | Preview shows rows matching filter; no SQL entered by user
2 | P0-6-D-002 | Report Designer & Export | E2E | P2-High | Export report as PDF | ⬜ NOT RUN | Report defined | 1. POST /reports/definitions/:id/run {format:'PDF'} 2. Download file | PDF downloaded; has header with report name + date; rows formatted as table
3 | P0-6-D-003 | Report Designer & Export | E2E | P2-High | Export report as XLSX | ⬜ NOT RUN | Report defined | 1. POST /reports/definitions/:id/run {format:'XLSX'} | XLSX file; header row styled; auto-filter enabled; no formula errors
4 | P0-6-D-004 | Report Designer & Export | E2E | P3-Medium | Schedule report — weekly delivery | ⬜ NOT RUN | Report defined; SMTP configured | 1. Create schedule: weekly Monday 08:00; recipient role 'Admin'; format PDF 2. Trigger manually | Email delivered to all Admin users with PDF attachment; run_log records row_count
5 | P0-6-D-005 | Report Designer & Export | Integration | P2-High | Skip-if-empty schedule — no email when 0 rows | ⬜ NOT RUN | Schedule with skip_if_empty=true; empty result set | 1. Trigger scheduled run | No email sent; run_log status=SKIPPED; row_count=0
BI Adapters
1 | P0-6-B-001 | BI Adapters | Integration | P2-High | Power BI Direct Query — eam_reporting role | ⬜ NOT RUN | PostgreSQL read replica; eam_reporting role created | 1. Connect via psql as eam_reporting 2. SELECT * FROM rpt_tenant_X_work_orders 3. Try UPDATE | SELECT succeeds with tenant-scoped data; UPDATE returns permission denied
2 | P0-6-B-002 | BI Adapters | Integration | P2-High | Tableau WDC schema endpoint | ⬜ NOT RUN | WDC endpoint deployed | 1. GET /reporting/tableau-wdc/work_orders/schema | Returns JSON with columns array; field types are correct Tableau types
3 | P0-6-B-003 | BI Adapters | Integration | P2-High | Tableau WDC data endpoint — pagination | ⬜ NOT RUN | work_orders subject has > 100 rows | 1. GET /reporting/tableau-wdc/work_orders/data?page=1&limit=100 | Returns 100 rows; has_more=true; page=2 returns next batch
4 | P0-6-B-004 | BI Adapters | Integration | P3-Medium | Qlik export generates CSV to S3 | ⬜ NOT RUN | Qlik adapter configured | 1. POST /admin/reporting/bi/qlik/export/work_orders | CSV file in S3 at configured prefix; file contains correct tenant data
5 | P0-6-B-005 | BI Adapters | Integration | P3-Medium | BIRT rptdesign upload and render | ⬜ NOT RUN | BIRT runtime container running | 1. Upload sample.rptdesign 2. GET /admin/reporting/birt/:id/run?format=PDF | PDF rendered by BIRT runtime; proxied back to caller

## 🖥️ P0-7 Dashboard
EAM Phase 0 — P0-7 User Dashboard & Active-User Collaboration ¦ Test Cases
Workstream: P0-7 • Pass: =COUNTIF(G5:G5000,"✅ PASS") ¦ Fail: =COUNTIF(G5:G5000,"❌ FAIL") ¦ Total: =COUNTA(B5:B5000)
# | Test ID | Category | Type | Priority | Test Title | Status | Preconditions | Test Steps | Expected Result | Actual Result | Tester | Date Tested | Notes / Defect Ref
Dashboard Configuration
1 | P0-7-D-001 | Dashboard Configuration | E2E | P2-High | Role-default dashboard shown to new user | ⬜ NOT RUN | Admin has set default layout for 'Technician' role with 2 widgets | 1. Create new user with Technician role 2. Login | Dashboard shows 2 pre-configured widgets; no manual setup required
2 | P0-7-D-002 | Dashboard Configuration | E2E | P2-High | User personalises layout — persists across sessions | ⬜ NOT RUN | User logged in | 1. Drag widget to new position 2. Logout 3. Login again | Widget in new position; layout saved to user_dashboards
3 | P0-7-D-003 | Dashboard Configuration | E2E | P2-High | User resets to role default | ⬜ NOT RUN | User has personalised layout | 1. Click 'Reset to Default' 2. Confirm | Layout reverts to role default; user_dashboards row updated
4 | P0-7-D-004 | Dashboard Configuration | E2E | P3-Medium | Multiple named dashboard tabs | ⬜ NOT RUN | User logged in | 1. Add new tab named 'Procurement' 2. Add widgets to it 3. Switch tabs | Both tabs persist; each has independent widget layout
Widget Functionality
1 | P0-7-W-001 | Widget Functionality | Integration | P2-High | KPI tile shows correct aggregate value | ⬜ NOT RUN | Work orders in DB; KPI tile configured for count of OPEN WOs | 1. Open dashboard with KPI tile | Tile shows correct count matching DB query; refreshes per configured interval
2 | P0-7-W-002 | Widget Functionality | Integration | P2-High | List widget shows top-N records | ⬜ NOT RUN | List widget: entity=WorkOrder, filter={status:OPEN}, max_rows=5 | 1. Open dashboard | Up to 5 open WOs shown; click on row navigates to WO detail
3 | P0-7-W-003 | Widget Functionality | Performance | P2-High | Slow widget does not block other widgets | ⬜ NOT RUN | One widget configured with a slow query (forced via mock) | 1. Open dashboard 2. Observe load order | Fast widgets show data while slow widget shows skeleton; page not blocked
4 | P0-7-W-004 | Widget Functionality | Integration | P3-Medium | Chart widget auto-refreshes | ⬜ NOT RUN | Chart widget with refresh_interval=60s | 1. Open dashboard 2. Wait 60+ seconds 3. Observe network requests | New data request fired after 60s; chart updates without page reload
5 | P0-7-W-005 | Widget Functionality | Integration | P2-High | Active Users widget shows online users | ⬜ NOT RUN | Two users logged in (Playwright 2-tab test) | 1. Both users open dashboard 2. Check Active Users widget | Both users appear as ONLINE; status updates within heartbeat interval
Presence & Chat
1 | P0-7-C-001 | Presence & Chat | E2E | P1-Critical | Direct message delivered in real time | ⬜ NOT RUN | Two browser sessions (User A and User B) | 1. User A sends message to User B 2. Observe User B's chat window | Message appears in User B's chat within 2 seconds
2 | P0-7-C-002 | Presence & Chat | E2E | P2-High | Unread badge increments on new message | ⬜ NOT RUN | User B has chat closed | 1. User A sends message to User B | User B's bell/chat icon shows unread badge count = 1
3 | P0-7-C-003 | Presence & Chat | E2E | P2-High | Context link in chat from WO detail page | ⬜ NOT RUN | WO-001 detail page | 1. User A clicks Share from WO-001 2. Selects User B 3. Sends | User B receives message with WO-001 link; clicking link navigates to WO-001
4 | P0-7-C-004 | Presence & Chat | Integration | P2-High | User goes offline after disconnect | ⬜ NOT RUN | User A connected | 1. User A closes browser tab 2. Wait > 5s grace period 3. Check presence | User A presence status=OFFLINE; Active Users widget updates
5 | P0-7-C-005 | Presence & Chat | Integration | P3-Medium | DND status visible to others | ⬜ NOT RUN | User A sets DND | 1. User A emits status:update {status:DND} 2. User B checks Active Users | User A shown with amber indicator

## 📧 P0-8 Notifications
EAM Phase 0 — P0-8 Email Notification Framework ¦ Test Cases
Workstream: P0-8 • Pass: =COUNTIF(G5:G5000,"✅ PASS") ¦ Fail: =COUNTIF(G5:G5000,"❌ FAIL") ¦ Total: =COUNTA(B5:B5000)
# | Test ID | Category | Type | Priority | Test Title | Status | Preconditions | Test Steps | Expected Result | Actual Result | Tester | Date Tested | Notes / Defect Ref
Email Delivery
1 | P0-8-E-001 | Email Delivery | Integration | P1-Critical | Email sent on WO_ASSIGNED event | ⬜ NOT RUN | Notification trigger active for WO_ASSIGNED; Mailhog SMTP configured | 1. Create WO with assigned_to_user_id set 2. Check Mailhog inbox | Email arrives within 30s; subject and body contain correct WO number and assignee name
2 | P0-8-E-002 | Email Delivery | Integration | P1-Critical | Merge fields render correctly in template | ⬜ NOT RUN | Template with {{workorder.num}}, {{asset.description}}, {{assignee.name}} | 1. Trigger email event 2. Inspect email body | All merge fields replaced with actual values; no {{placeholder}} strings visible
3 | P0-8-E-003 | Email Delivery | Integration | P2-High | Plain-text fallback sent alongside HTML | ⬜ NOT RUN | Email client set to plain text only | 1. Inspect raw email MIME | Email has both text/html and text/plain parts
4 | P0-8-E-004 | Email Delivery | Integration | P2-High | Hard SMTP bounce marks user email_bounced | ⬜ NOT RUN | SMTP mock returns 550 permanent failure | 1. Send notification to bouncing address | delivery_log status=FAILED; user.email_bounced=true; admin alerted
5 | P0-8-E-005 | Email Delivery | Integration | P2-High | Delivery log records every send | ⬜ NOT RUN | Multiple notifications triggered | 1. GET /admin/notifications/delivery-log | All send attempts logged with status, timestamp, recipient, event type
Triggers & Conditions
1 | P0-8-T-001 | Triggers & Conditions | Integration | P1-Critical | Conditional trigger — only fires when condition met | ⬜ NOT RUN | Trigger for PR_APPROVED with condition totalcost>100000 | 1. Approve PR with totalcost=80000 → check for email 2. Approve PR with totalcost=150000 → check | Step 1: no email. Step 2: email sent
2 | P0-8-T-002 | Triggers & Conditions | Integration | P2-High | Rate limiting — bulk update produces digest not N emails | ⬜ NOT RUN | Trigger with rate_limit: max=10 per 60s; 50 WOs updated | 1. Update 50 WOs to APPR status 2. Check emails | ≤ 10 emails (or 1 digest) sent; not 50
3 | P0-8-T-003 | Triggers & Conditions | Integration | P2-High | Digest mode — batched email sent after window | ⬜ NOT RUN | Trigger with digest_config enabled; window=5min | 1. Fire same event 5 times within window 2. Wait for window to close | 1 digest email sent listing all 5 events; not 5 separate emails
4 | P0-8-T-004 | Triggers & Conditions | Integration | P3-Medium | Admin disables trigger — no notifications fired | ⬜ NOT RUN | Active trigger | 1. Set trigger is_active=false 2. Fire triggering event | No email; no in-app notification; no delivery log entry
In-App Notifications
1 | P0-8-I-001 | In-App Notifications | E2E | P1-Critical | In-app notification delivered in real time | ⬜ NOT RUN | User logged in; WS connection active | 1. Trigger event (WO assigned to user) 2. Observe notification bell | Bell badge increments within 2s; notification visible in drawer
2 | P0-8-I-002 | In-App Notifications | E2E | P2-High | User unsubscribes from email — still gets in-app | ⬜ NOT RUN | User has disabled email for WO_ASSIGNED | 1. Assign WO to user | No email; in-app notification still delivered
3 | P0-8-I-003 | In-App Notifications | Integration | P2-High | Mark notification read | ⬜ NOT RUN | User has unread notification | 1. POST /notifications/:id/read 2. GET /notifications | is_read=true; read_at set; unread count decrements
4 | P0-8-I-004 | In-App Notifications | Integration | P3-Medium | Mandatory trigger cannot be disabled by user | ⬜ NOT RUN | System trigger is_mandatory=true | 1. User tries to disable via PUT /users/me/notification-preferences | Preference update rejected for mandatory trigger; toggle locked in UI
Admin Configuration
1 | P0-8-A-001 | Admin Configuration | E2E | P2-High | SMTP configuration + test send | ⬜ NOT RUN | Admin on SMTP config page; Mailhog available | 1. Enter SMTP credentials 2. Click Send Test Email | Test email arrives in Mailhog; success message shown in UI
2 | P0-8-A-002 | Admin Configuration | E2E | P2-High | Create new notification trigger with custom template | ⬜ NOT RUN | Admin on Triggers page | 1. Create trigger for custom event type 2. Select custom template 3. Activate | Trigger active; fires correctly on next matching event; no code change required
3 | P0-8-A-003 | Admin Configuration | E2E | P3-Medium | Template preview renders correctly | ⬜ NOT RUN | Admin in Template editor | 1. Edit template 2. Click Preview 3. Click Send Preview Email | Preview renders with sample data; email arrives at admin's inbox

## 🧩 Integration Sprint
EAM Phase 0 — Integration Sprint — End-to-End & Non-Functional ¦ Test Cases
Workstream: INT • Pass: =COUNTIF(G5:G5000,"✅ PASS") ¦ Fail: =COUNTIF(G5:G5000,"❌ FAIL") ¦ Total: =COUNTA(B5:B5000)
# | Test ID | Category | Type | Priority | Test Title | Status | Preconditions | Test Steps | Expected Result | Actual Result | Tester | Date Tested | Notes / Defect Ref
End-to-End Scenario
1 | INT-E2E-001 | End-to-End Scenario | E2E | P1-Critical | Full Phase 0 integration scenario — Step 1: LDAP sync | ⬜ NOT RUN | All 8 services running; mock LDAP server; Playwright test | 1. Admin logs in 2. Configures LDAP provider 3. Triggers sync | New user testtech@eam.local appears in Users list with auth_source=LDAP
2 | INT-E2E-002 | End-to-End Scenario | E2E | P1-Critical | Integration scenario — Step 2: Custom field added | ⬜ NOT RUN | Previous step passed | 1. Admin adds text field 'Equipment Code' to Asset entity, marks required | Field on Asset form; saving without it fails at API level
3 | INT-E2E-003 | End-to-End Scenario | E2E | P1-Critical | Integration scenario — Step 3: Workflow created | ⬜ NOT RUN | Previous step passed | 1. Admin creates SR workflow: START → TASK (Supervisor) → END 2. Binds to SR_CREATED | Workflow published; binding active
4 | INT-E2E-004 | End-to-End Scenario | E2E | P1-Critical | Integration scenario — Step 4: SR created starts workflow | ⬜ NOT RUN | Previous step passed | 1. testtech@eam.local creates Service Request | Workflow instance starts; task created for Supervisor role
5 | INT-E2E-005 | End-to-End Scenario | E2E | P1-Critical | Integration scenario — Step 5: In-app notification received | ⬜ NOT RUN | Previous step passed | 1. Check Supervisor user's notifications | In-app notification 'New SR task assigned' appears in bell within 5s
6 | INT-E2E-006 | End-to-End Scenario | E2E | P1-Critical | Integration scenario — Step 6: Attachment uploaded + scanned | ⬜ NOT RUN | Previous step passed | 1. testtech uploads PDF to SR 2. Wait for scan worker | Attachment scan_status=CLEAN; download URL works
7 | INT-E2E-007 | End-to-End Scenario | E2E | P1-Critical | Integration scenario — Step 7: Workflow task approved | ⬜ NOT RUN | Previous step passed | 1. Supervisor approves task via SR workflow panel | Instance status=COMPLETED; history shows APPROVED; SR status updated
8 | INT-E2E-008 | End-to-End Scenario | E2E | P1-Critical | Integration scenario — Step 8: SR appears in report | ⬜ NOT RUN | Previous step passed | 1. Admin runs Service Requests report 2. Exports PDF | New SR in results; PDF export successful
9 | INT-E2E-009 | End-to-End Scenario | E2E | P1-Critical | Integration scenario — Step 9: Dashboard KPI updates | ⬜ NOT RUN | testtech dashboard has KPI tile 'My Open SRs' | 1. Check KPI tile value | Count reflects newly created SR
10 | INT-E2E-010 | End-to-End Scenario | E2E | P1-Critical | Integration scenario — Step 10: Chat with record link | ⬜ NOT RUN | Previous step passed | 1. testtech sends chat message to Supervisor with SR link | Message delivered <2s; SR link renders in message; both parties see it
Performance / Load
1 | INT-P-001 | Performance / Load | Performance | P1-Critical | k6 load test — p50 < 800ms | ⬜ NOT RUN | k6 installed; staging environment running; 100 VUs | Run k6 load-tests/phase0-baseline.js | http_req_duration p(50) < 800ms threshold met
2 | INT-P-002 | Performance / Load | Performance | P1-Critical | k6 load test — p95 < 2000ms | ⬜ NOT RUN | Same as above | Run k6 load-tests/phase0-baseline.js | http_req_duration p(95) < 2000ms threshold met
3 | INT-P-003 | Performance / Load | Performance | P1-Critical | k6 load test — error rate < 1% | ⬜ NOT RUN | Same as above | Run k6 load-tests/phase0-baseline.js | http_req_failed < 1% threshold met
4 | INT-P-004 | Performance / Load | Performance | P2-High | Dashboard widgets load independently under load | ⬜ NOT RUN | 100 concurrent users on dashboard | Observe widget load order via browser perf trace | No widget blocks another; each loads within its individual SLA
5 | INT-P-005 | Performance / Load | Performance | P2-High | 5000 WebSocket connections held without degradation | ⬜ NOT RUN | k6 WebSocket test script | Connect 5000 clients; send heartbeat every 30s for 5 min | All connections maintained; server memory stable; no OOM
Security Baseline
1 | INT-S-001 | Security Baseline | Security | P1-Critical | Security headers present on all API responses | ⬜ NOT RUN | Playwright security header check | 1. Make GET /auth/me 2. Inspect response headers | X-Content-Type-Options, X-Frame-Options, Strict-Transport-Security, CSP all present
2 | INT-S-002 | Security Baseline | Security | P1-Critical | JWT uses RS256 (not HS256) | ⬜ NOT RUN | Login and get token | 1. Decode JWT header 2. Check alg field | alg=RS256
3 | INT-S-003 | Security Baseline | Security | P1-Critical | Rate limiting on /auth/* routes | ⬜ NOT RUN | Unauthenticated client | 1. Send 101 POST /auth/login requests in 60s | 101st request returns 429 Too Many Requests
4 | INT-S-004 | Security Baseline | Security | P1-Critical | CORS — requests from non-whitelisted origin rejected | ⬜ NOT RUN | API running with ALLOWED_ORIGINS=https://eam.example.com | 1. Make API request with Origin: https://attacker.com | Response has no Access-Control-Allow-Origin header; browser blocks request
5 | INT-S-005 | Security Baseline | Security | P2-High | pnpm audit passes with no high/critical vulnerabilities | ⬜ NOT RUN | CI pipeline | 1. Run pnpm audit --audit-level=high | Exit code 0; no high or critical findings
6 | INT-S-006 | Security Baseline | Security | P2-High | Audit log entries for all sensitive actions | ⬜ NOT RUN | DB running | 1. Perform: login, failed login, role change, file download, DDL change 2. Query audit_logs | Entry exists for each action with user_id, ip_address, action, timestamp
7 | INT-S-007 | Security Baseline | Security | P2-High | File upload size limit enforced | ⬜ NOT RUN | MAX_UPLOAD_MB=50 | 1. Attempt presign for 60MB file | 422 with size_exceeded error; no presigned URL issued
Phase 0 Exit Gate
1 | INT-G-001 | Phase 0 Exit Gate | Manual | P1-Critical | All P0-1 acceptance criteria passed | ⬜ NOT RUN | P0-1 test sheet complete | Review P0-1 sheet — all marked ✅ PASS or ⏭️ SKIP with justification | 0 ❌ FAIL in P0-1 sheet
2 | INT-G-002 | Phase 0 Exit Gate | Manual | P1-Critical | All P0-2 acceptance criteria passed | ⬜ NOT RUN |  | Review P0-2 sheet | 0 ❌ FAIL in P0-2 sheet
3 | INT-G-003 | Phase 0 Exit Gate | Manual | P1-Critical | All P0-3 acceptance criteria passed | ⬜ NOT RUN |  | Review P0-3 sheet | 0 ❌ FAIL in P0-3 sheet
4 | INT-G-004 | Phase 0 Exit Gate | Manual | P1-Critical | All P0-4 acceptance criteria passed | ⬜ NOT RUN |  | Review P0-4 sheet | 0 ❌ FAIL in P0-4 sheet
5 | INT-G-005 | Phase 0 Exit Gate | Manual | P1-Critical | All P0-5 acceptance criteria passed | ⬜ NOT RUN |  | Review P0-5 sheet | 0 ❌ FAIL in P0-5 sheet
6 | INT-G-006 | Phase 0 Exit Gate | Manual | P1-Critical | All P0-6 acceptance criteria passed | ⬜ NOT RUN |  | Review P0-6 sheet | 0 ❌ FAIL in P0-6 sheet
7 | INT-G-007 | Phase 0 Exit Gate | Manual | P1-Critical | All P0-7 acceptance criteria passed | ⬜ NOT RUN |  | Review P0-7 sheet | 0 ❌ FAIL in P0-7 sheet
8 | INT-G-008 | Phase 0 Exit Gate | Manual | P1-Critical | All P0-8 acceptance criteria passed | ⬜ NOT RUN |  | Review P0-8 sheet | 0 ❌ FAIL in P0-8 sheet
9 | INT-G-009 | Phase 0 Exit Gate | Manual | P1-Critical | Load test all thresholds passing (INT-P-001 to INT-P-003) | ⬜ NOT RUN |  | Run k6 test and confirm | All 3 perf thresholds GREEN
10 | INT-G-010 | Phase 0 Exit Gate | Manual | P1-Critical | Security baseline complete (INT-S-001 to INT-S-007) | ⬜ NOT RUN |  | Review INT-S tests | All critical security tests PASS
11 | INT-G-011 | Phase 0 Exit Gate | Manual | P1-Critical | Engineering Lead + Product Sponsor sign-off | ⬜ NOT RUN |  | Formal review meeting | Sign-off recorded; Phase 1 sprint 1 scheduled

## 🐛 Defect Log
EAM Phase 0 — Defect Log
Defect ID | Test Case ID | Workstream | Severity | Title | Steps to Reproduce | Expected | Actual | Environment | Assigned To | Status | Fix Version | Notes